## Summary
Enterprise Data Modernization & AI Readiness ¦ 12-Month Program Summary
KEY MILESTONES BY MONTH
March 2026 (M1) | Phase 1 Kickoff ¦ Scoring framework approved ¦ DataHub deployed ¦ RACI finalized ¦ LOB data owners identified
April 2026 (M2) | Mainframe audit underway ¦ AWS/Snowflake inventory ¦ Business glossary 50% ¦ Training curriculum drafted
May 2026 (M3) | Phase 1 Exit Gate (Week 12) ¦ Scoring framework validated ¦ Phase 2 kickoff ¦ Vendor RFP finalized
June 2026 (M4) | Automated scoring implemented ¦ 300+ datasets scored ¦ DRIA tool live ¦ 30%+ data owner sign-offs
July 2026 (M5) | DRIA sign-offs >80% ¦ Prioritized backlog published ¦ Phase 3 intake finalized ¦ SageMaker/Glue POC
Aug 2026 (M6) | Phase 2 Exit Gate (Week 24) ¦ Master scorecard approved ¦ Vendor contracts signed ¦ Phase 3 technical kickoff
Sept 2026 (M7) | Entity extraction pilots running ¦ Vector embedding design ¦ Data classification taxonomy ¦ Training >30% completion
Oct 2026 (M8) | NLP classification live ¦ Metadata enrichment pipeline ¦ 3+ LOBs publishing data products ¦ Training >60%
Nov 2026 (M9) | Agent readiness certification (50 datasets) ¦ RLS/CLS implementation ¦ Compliance audit trail live ¦ Training >80%
Dec 2026 (M10) | Phase 3 Exit Gate (Week 34) ¦ 100+ agent-ready datasets ¦ Ops monitoring setup ¦ V1 data mesh operational
Jan 2027 (M11) | Phase 4: Gamification/adoption incentives ¦ Innovation pilot approvals ¦ Legacy systems retirement ¦ Knowledge transfer
Feb 2027 (M12) | Regulatory certification complete ¦ Phase 4 Exit Gate (Week 48) ¦ Program closeout ¦ V2 business case launch
CRITICAL PATH ITEMS (No Flexibility)
• Phase 1 Exit Gate (Week 12): Scoring framework + RACI finalized OR risk full program delay
• DRIA Sign-up Momentum (Weeks 14-18): <50% sign-up = signal data owner resistance; escalate to SVPs
• Vendor Selection (Week 20): 30-day contract negotiation window; any delay pushes Phase 3 start to Week 26+
• Agent Readiness Certification (Week 30): <75 datasets ready = Phase 4 starts late OR reduces AI scope
• Regulatory Certification (Week 41): BCBS 239/GDPR audit failures = go-live blocked; must have zero critical findings
KEY RELATIONSHIPS TO ESTABLISH (By Month)
M1-2 | 13 LOB SVPs/Heads | Establish RACI ownership; set expectations for data stewards
M1-2 | CRO/Chief Compliance | BCBS 239 audit trail design; get regulatory blessing
M1-3 | Chief Data Officer | Governance charter; metadata strategy alignment; budget approval
M2-4 | Top 3 LOB Data Stewards | Build trust; make them change champions; drive DRIA adoption
M3-5 | AWS/Databricks/Collibra Partners | Embedded technical team members; joint architecture decisions
M4-6 | CFO & Finance | Cost-benefit modeling; budget tracking; ROI validation
M5-7 | Change & Communications Team | Training curriculum; adoption metrics; executive storytelling
M6-8 | Data Products/Mesh Champions (Auto, Credit Card, Risk) | Co-design data product standards; pilot publishing
M8-10 | AI/ML Lab & SageMaker Team | Agent readiness criteria; AI safety gates; model governance
M10-11 | COO & Ops Leadership | Permanent team charter; ops funding; governance transition
M11-12 | Board/Investor Relations | V1 success story; V2 roadmap approval; investor confidence

## 12-Month Plan
Week # | Dates | Phase | Focus Area | Key Actions (2-3 per week) | Meetings to Schedule | Relationships to Build | Decisions to Drive | Deliverables Due | Risk Watch Items
1 | 03/02 - 03/06 | Phase 1 | Scoring Framework Finalization | H1: Meet Data Architects; review Four Pillars scoring criteria against BCBS 239 | Setup: 1-on-1 with Compliance Officer; intro call with 13 LOB heads | Build relationships with Data Governance team; establish with SME champions in top 3 LOBs | Approve scoring model; confirm enterprise metadata standard approach | Framework doc (draft); kickoff presentation
2 | 03/09 - 03/13 | Phase 1 | Mainframe Data Audit Kickoff | H2: Launch mainframe crawl across COBOL systems; start AWS/Snowflake inventory | Tech Council (bi-weekly); schedule Mainframe SME interviews (4-5 key contacts) | Identify Mainframe data owners in each LOB; connect with AWS Solution Architects | Define mainframe crawl scope; confirm AWS inventory tool setup | Mainframe crawl plan; AWS account access confirmed
3 | 03/16 - 03/20 | Phase 1 | DataHub & Metadata Schema | H3: Deploy Collibra/Alation; finalize enterprise metadata schema per ISO 11179 | Setup DataHub: confirm with architect team; schedule data model review | Establish relationship with Collibra implementation partner; meet cloud DBA for integration | Approve metadata schema v1; confirm DataHub deployment timeline | DataHub deployment checklist; metadata schema v1
4 | 03/23 - 03/27 | Phase 1 | Data Owner Identification & RACI | H4: Complete RACI matrix with 13 LOB heads; assign data stewards; establish governance council | SteerCo kickoff (monthly steering); Risk & Compliance intro (bi-weekly cadence); Tech Council standoff (bi-weekly) | Lock in relationships with 13 LOB heads; meet CFO/Budget owner; identify Change sponsor in COO org | Final RACI approved by SVPs; confirm governance council charters (SteerCo, Tech, Risk&Comp, Working Team) | Signed RACI matrix; governance council charters | RACI conflicts between LOBs; unclear accountabilities
5 | 03/30 - 04/03 | Phase 1 | Ops LOB Pilot Expansion | M5: Expand Ops LOB pilot artifacts (data lineage, PII masking) for global template reuse | Weekly with Ops LOB lead; kick-off with ML/NLP vendor for Phase 3 scope | Ops LOB data steward as core partner; intro with ML vendor (finalists from RFP) | Approve Ops pilot artifacts as global template; vendor pre-selection (3 finalists) | Ops pilot template doc; vendor shortlist (3 companies)
6 | 04/06 - 04/10 | Phase 1 | Phase 1 Mid-Point Check | M6: Validate progress on scoring framework, metadata schema, DataHub deployment; flag risks | SteerCo mid-phase update; Risk & Compliance checkpoint on lineage audit trail setup | One-on-ones with 3-4 LOBs most resistant to data sharing; gauge sentiment | Approve Phase 1 extension if mainframe crawl behind schedule | Phase 1 progress report; risk mitigation plans
7 | 04/13 - 04/17 | Phase 1 | Cloud Source Inventory & PII Classification | M7: Complete AWS/Snowflake crawl; finalize PII/MNPI classification rules with Compliance | Meet with AWS Glue team for automated crawling; Compliance Officer for masking rules | AWS Solution Architect embedded in weekly Tech Council | Approve AWS crawl results + confidence levels; sign-off on masking rules | Cloud source inventory (all 300+ datasets); PII classification matrix
8 | 04/20 - 04/24 | Phase 1 | Business Glossary (80%) & Quality Baseline | H8: Draft business glossary (200+ terms); launch DQ baseline assessment on 50 datasets | Glossary review workshop with SME champions from 5 major LOBs; DQ assessment kickoff | Identify business glossary SPOC from each LOB; DQ analyst as core team | Approve glossary governance process; DQ scoring methodology signed by Compliance | Draft glossary (80%); DQ baseline report (50 datasets)
9 | 04/27 - 05/01 | Phase 1 | Security & Compliance Foundations | H9: Finalize Zero Trust architecture, RLS/CLS policies, audit trail for BCBS 239 compliance | Security deep-dive with CISOs team; Compliance validation of audit trail design | Security Officer as core working team member; establish with Legal on GDPR/CCPA | Approve security architecture + audit trail design; confirm Legal review timeline | Security architecture doc; audit trail proof-of-concept
10 | 05/04 - 05/08 | Phase 1 | Change Readiness & Training Curriculum | M10: Conduct change readiness survey of 13 LOBs; draft training curriculum (DataHub/DRIA) | Post survey with LOBs (2-3 interviews each); Change Lead outreach across LOBs | Identify change champions in each LOB; meet HR/Learning & Development for training logistics | Approve change readiness report; confirm training curriculum outline | Change readiness report; training curriculum draft
11 | 05/11 - 05/15 | Phase 1 | KPI Dashboard (Draft) & Phase 1 Prep for Gate | M11: Define success metrics (# datasets, adoption, quality); prepare Phase 1 exit gate | Analytics/BI team for dashboard design; final checkpoint with all working team leads | Establish with CFO/Finance for cost tracking | Approve KPI definitions; confirm Phase 1 exit gate criteria with SteerCo | KPI dashboard template; Phase 1 exit gate checklist
12 | 05/18 - 05/22 | Phase 1 | PHASE 1 EXIT GATE REVIEW | H12: SteerCo approval to proceed to Phase 2; confirm scoring framework, data owner engagement, compliance | SteerCo Phase 1 exit gate meeting; Tech Council technical review; Risk & Compliance sign-off | All LOB heads present for Phase 1 retrospective and Phase 2 kick-off | Final sign-offs on Phase 1 deliverables; approval to proceed to Phase 2 | SteerCo gate sign-off memo; Phase 2 kickoff materials | Mainframe crawl incomplete; delays risk Phase 2 start
13 | 05/25 - 05/29 | Phase 2 | Scoring Engine Architecture & Phase 2 Kickoff | H13: Design automated scoring pipeline (SageMaker/Glue); present Phase 2 roadmap to SteerCo | Tech Council: scoring architecture deep-dive; working team expanded for Phase 2 | Deeper engagement with ML/NLP vendor; AWS ML specialists on Tech Council | Approve scoring engine architecture; confirm Phase 2 team staffing | Scoring architecture design; Phase 2 roadmap presentation
14 | 06/01 - 06/05 | Phase 2 | Scoring Logic & DRIA Tool Setup | H14: Build automated scoring rules; set up DRIA tool for data owner acceptance + sign-off | ML Engineer lead on scoring implementation; DRIA vendor kickoff (Collibra/custom build) | Data Engineer as DRIA technical lead; identify 'super-user' data owners for pilot | Approve scoring rules logic; confirm DRIA design (workflow, notifications, SLA) | Scoring rules document; DRIA MVP design
15 | 06/08 - 06/12 | Phase 2 | Conflict Resolution & Tech Council Depth | M15: Address scoring disputes via Tech Council; refine scoring rules based on feedback | Expanded Tech Council sessions for score validation; working team daily standups | Deeper relationships with data owners from Auto/Credit Card (highest resistance risk) | Resolve top 10 scoring disputes; approve refined rules | Scoring dispute resolution log; refined scoring rules v1.1
16 | 06/15 - 06/19 | Phase 2 | Score All 300+ Datasets & Data Owner Engagement | H16: Run automated scoring across enterprise; begin DRIA signoff process with 100 data owners | Data owner kickoff calls (batch process: 10-20 per week); DRIA training sessions begin | Individual 1-on-1s with top 15 high-friction data owners; establish trust | Approve master scorecard; confirm first cohort of DRIA sign-offs (30+) | Master scorecard (all 300+ datasets); DRIA registrations (30+ owners signed) | Data owner resistance to scoring; low DRIA sign-up rates
17 | 06/22 - 06/26 | Phase 2 | Prioritized Backlog & Phase 3 Intake | M17: Publish prioritized backlog; identify Phase 3 intake list (top 100 datasets for enrichment) | Prioritization workshop with SteerCo + Tech Council; Phase 3 planning kickoff | Phase 3 technical leads onboard (ML/NLP vendors, Data Engineers) | Approve prioritized backlog + Phase 3 intake list | Prioritized backlog document; Phase 3 intake list
18 | 06/29 - 07/03 | Phase 2 | Business Glossary (100%) & SLA Framework | M18: Complete 100% business glossary; define Data Mesh SLAs for datasets | Final glossary review + FIBO mapping sessions; SLA co-design with LOBs | Data Architect leads glossary completion; Product Manager leads SLA definition | Approve final glossary + FIBO mapping; SLA framework signed by LOB heads | Complete glossary (published to DataHub); SLA framework document
19 | 07/06 - 07/10 | Phase 2 | Sensitivity Validation & Lineage Audit | H19: Validate PII/MNPI detection accuracy (AWS Comprehend); audit BCBS 239 lineage for top 50 datasets | Compliance Officer leads sensitivity review; external audit firm for lineage validation | Compliance/Risk team partnership deepens; audit firm as advisor on regulatory posture | Approve sensitivity detection rules (>95% accuracy); confirm lineage audit results | Validated sensitivity matrix; lineage audit report (top 50 datasets)
20 | 07/13 - 07/17 | Phase 2 | Vendor Selection & Cost-Benefit Analysis | M20: Select NLP/ML vendors; finalize Phase 3+4 business case (ROI, cost, timeline) | Vendor finalist presentations + evaluation (3 days); business case workshop with finance | Vendor relationship management begins; CFO/Finance partner on cost-benefit | Approve vendor contracts + SLAs; business case V1 approved by SteerCo | Signed vendor contracts; Phase 3+4 business case presentation
21 | 07/20 - 07/24 | Phase 2 | SageMaker/Glue Pipeline Setup & DRIA Momentum | H21: Configure SageMaker/Glue for Phase 3 enrichment pipelines; push DRIA sign-offs to 80%+ | Data Engineer + AWS ML team build & test pipelines; DRIA escalation calls for remaining owners | AWS ML specialists embedded in daily standups; pressure on resistant data owners via LOB heads | Approve pipeline proof-of-concept; confirm 80%+ DRIA registration target | SageMaker/Glue pipeline POC; DRIA registration at 80%+
22 | 07/27 - 07/31 | Phase 2 | Phase 2 Mid-Point & Adoption Metrics | M22: Validate Phase 2 progress; establish adoption baseline (KPIs, steward engagement, data access patterns) | Mid-phase checkpoint with SteerCo; adoption metrics workshop with Change Lead | One-on-ones with LOBs not yet signed up in DRIA; data steward focus groups | Approve adoption baseline metrics; identify Phase 2 accelerators | Phase 2 progress report; adoption baseline metrics report
23 | 08/03 - 08/07 | Phase 2 | Risk Register & Compliance Update | M23: Finalize risk register for BCBS 239; ensure compliance with GDPR/CCPA consent management | Risk & Compliance deep-dive on emerging risks (tool failures, data gaps); Legal review GDPR/CCPA | Compliance Officer leads risk register maintenance | Approve updated risk register; Legal signs off on consent management approach | Updated risk register; Legal memo on GDPR/CCPA compliance
24 | 08/10 - 08/14 | Phase 2 | PHASE 2 EXIT GATE & PHASE 3 KICKOFF | H24: SteerCo approval for Phase 3; present prioritized backlog, business case, Phase 3 team | SteerCo Phase 2 exit gate (major milestone); Phase 3 kickoff with expanded team | Phase 3 tech leads formally onboarded; all 13 LOB heads briefed on Phase 3 roadmap | SteerCo approval to proceed to Phase 3; Phase 3 budget approved; vendor contracts active | SteerCo gate sign-off; Phase 3 kickoff charter | Vendor readiness delays; SageMaker/Glue pipeline POC at risk
25 | 08/17 - 08/21 | Phase 3 | NLP Entity Extraction & Vector Embedding Kickoff | H25: Launch entity extraction pilots (SageMaker + vendor NLP); begin vector embedding design | ML Engineer + vendor NLP team kick-off; vector DB evaluation (Pinecone/FAISS/Weaviate) | ML/NLP vendor embedded in daily standups | Approve entity extraction approach; select vector DB platform | Entity extraction pilot plan; vector DB selection memo
26 | 08/24 - 08/28 | Phase 3 | Data Classification & Sensitivity Detection | H26: Auto-classify 300+ datasets; refine sensitivity detection with NLP (PII, MNPI, confidential) | ML Engineer leads classification taxonomy; Compliance reviews sensitivity rules | Data Owners review classifications (sample set); Compliance as quality gate | Approve classification taxonomy; sign-off on sensitivity rules v2 | Classification taxonomy applied (300+ datasets); sensitivity rules v2
27 | 08/31 - 09/04 | Phase 3 | Metadata Enrichment & DRIA ML Integration | H27: Inject metadata into DataHub (definitions, lineage, quality, ownership); enable DRIA ML suggestions | Data Engineer leads enrichment pipeline; DRIA vendor for ML recommendation engine | DataHub/DRIA teams synchronized | Approve enrichment pipeline design; confirm DRIA ML recommendations launch | Metadata enrichment pipeline live; DRIA ML recommendations active
28 | 09/07 - 09/11 | Phase 3 | Cross-LOB Data Product Onboarding | M28: Facilitate Auto, Credit Card, Risk LOBs to publish data products (Data Mesh model); co-design SLAs | Product Manager leads data product design; LOB heads co-own product strategy | Deepen relationships with Product Managers from 3 pilot LOBs | Approve data product framework; 3 LOBs publish initial products | Data product framework doc; 3+ data products published
29 | 09/14 - 09/18 | Phase 3 | Change Management: LOB Training & Steward Adoption | H29: Deliver DataHub/DRIA/quality ownership training to all 13 LOBs; measure adoption >50% | Change Lead + Training team launch training program (in-person + virtual); track completion | Stewards from each LOB become change champions; daily feedback loops | Training completion >50%; identify top performers for center-of-excellence | Training completion report; adoption metrics >50%
30 | 09/21 - 09/25 | Phase 3 | SageMaker Agent Readiness Certification | H30: Validate top 50 datasets for AI agent consumption (accuracy, lineage, confidence scores, safety gates) | Data Architect leads certification; AI/ML team reviews agent readiness criteria | Agent readiness validation workshop with data owners + AI team | Approve agent readiness criteria; certify 50 datasets for AI agents | Agent readiness certification document; 50 certified datasets
31 | 09/28 - 10/02 | Phase 3 | Governance Policy Enforcement & RLS/CLS | H31: Implement automated access controls (row/column-level security); enforce ODRL policies at query time | Security Officer leads RLS/CLS implementation; Snowflake/Teradata DBAs execute | DBAs + Security team deeply embedded | Approve RLS/CLS implementation; policies enforced in production | RLS/CLS implementation proof-of-concept; policy enforcement rules
32 | 10/05 - 10/09 | Phase 3 | Phase 3 Mid-Point: Agent-Ready Ecosystem Status | M32: Validate progress on enrichment, embeddings, data products; confirm 100+ datasets approaching agent-ready state | Phase 3 mid-point checkpoint with SteerCo; Tech Council review of enrichment quality | One-on-ones with LOBs to validate data product quality + adoption | Approve Phase 3 acceleration if on track; identify bottlenecks | Phase 3 progress report; enrichment quality metrics
33 | 10/12 - 10/16 | Phase 3 | Compliance Audit Trail & BCBS 239 Certification | H33: Finalize audit logs for all data access, lineage changes, policy decisions; prepare BCBS 239 audit | Compliance Officer + external audit firm finalize audit trail; regulatory mock exam | Legal/Compliance partnership on final compliance posture | Approve audit trail completeness; regulatory mock exam results | Audit trail certification; BCBS 239 regulatory readiness memo
34 | 10/19 - 10/23 | Phase 3 | PHASE 3 EXIT GATE: AGENT-READY CERTIFICATION | H34: SteerCo approval of 100+ agent-ready datasets; confirm compliance, security, quality gates passed | SteerCo Phase 3 exit gate (critical milestone); executive sign-off on AI readiness | All LOB heads + 13 LOB data stewards attend Phase 3 retrospective | SteerCo approval for Phase 4; program continues to operational transition | SteerCo gate sign-off; Phase 3 retrospective & lessons learned | AI agent readiness certification gaps; compliance blockers
35 | 10/26 - 10/30 | Phase 3 | Operational Monitoring (24/7) & SLAs | H35: Establish on-call schedules (DataHub, DRIA, SageMaker); define incident response playbooks; target SLAs >99% | Data Engineer leads ops setup; incident command center design | Operations team hired/onboarded; escalation paths clear | Approve ops structure; SLAs >99% agreed with LOBs | Incident response playbooks; on-call schedule
36 | 11/02 - 11/06 | Phase 3 | Data Product Marketplace & LOB Autonomy | M36: Build self-service data product discovery portal; enable LOBs to autonomously publish/consume products | Product Manager leads marketplace design; LOBs begin publishing 5+ products | Deeper partnership with LOB product/engineering teams | Marketplace MVP live; 5+ products published | Marketplace platform live; product catalog
37 | 11/09 - 11/13 | Phase 4 | Gamification & Adoption Incentives | M37: Launch quality leaderboard (steward badges, recognition); measure engagement >60% | Change Lead leads gamification design; LOB stewards vote on incentives | Stewards become gamification champions | Approve incentive structure; leaderboard launched | Leaderboard live; engagement metrics >60%
38 | 11/16 - 11/20 | Phase 4 | Executive Readout & V2 Business Case | H38: Compile Phase 1-3 results (cost savings, quality uplift, adoption); prepare executive brief + V2 roadmap | Program Lead + Finance compile results; executive communications workshop | CEO/COO briefing prep | Approve results deck + V2 business case | Executive brief + board deck; V2 business case
39 | 11/23 - 11/27 | Phase 4 | Cross-LOB Innovation Pilots | M39: Identify 3-5 use cases leveraging enriched data (cross-sell, risk analytics, compliance); pilot approvals | Innovation workshop with LOB heads; pilot sponsor identification | LOB CIOs + business sponsors engaged | Approve 3-5 innovation pilots; secure funding/sponsorship | Innovation pilot charters (3-5 pilots)
40 | 11/30 - 12/04 | Phase 4 | Continuous Improvement & Governance Maturity | M40: Establish sprint-based improvement cycles; assess Data Mesh governance maturity; operationalize feedback loops | Continuous improvement retrospectives (bi-weekly); governance maturity assessment | Data Architect leads governance evolution | Approve operating model v1; improvement process launched | Operating model v1; improvement process documentation
41 | 12/07 - 12/11 | Phase 4 | Risk & Compliance Certification | H41: Final audit against BCBS 239, GDPR, CCPA, NIST AI RMF; regulatory sign-off for go-live | Compliance Officer + external auditors; regulatory engagement on final certification | Legal/Compliance/Risk alignment on all compliance artifacts | Regulatory certification approved; zero critical findings | Regulatory certification memo; final audit report | Regulatory findings require remediation; go-live delay risk
42 | 12/14 - 12/18 | Phase 4 | Legacy System Retirement Planning | M42: Phase out manual spreadsheets, legacy catalogs; migration to DataHub/DRIA; 90% legacy sunset | Program Lead + Data Engineer lead legacy decommissioning; LOB notifications | LOB IT teams engaged on legacy sunset | Approve legacy decommissioning plan; 90% systems migrated | Legacy decommissioning roadmap; migration tracking
43 | 12/21 - 12/25 | Phase 4 | Knowledge Transfer & Runbooks | M43: Codify all decisions, architectures, lessons learned; create runbooks for ops + stewards | Change Lead + Documentation team; steward input on runbooks | Subject matter experts across all teams document knowledge | Approve knowledge library; runbooks signed off by ops team | Knowledge library; operations runbooks
44 | 12/28 - 01/01 | Phase 4 | Final Stakeholder Alignment & Program Closeout | H44: Sync with SteerCo, Tech Council, Risk & Compliance on open items; prepare transition to ops | Final governance stakeholder alignment meeting; ops team charter review | All stakeholders confirm readiness for transition | All stakeholder sign-offs; ops team charter finalized | Stakeholder sign-off document; ops team charter
45 | 01/04 - 01/08 | Phase 4 | Transition to Operations | H45: Program transitions to permanent ops team; establish governance + team structure; document ROI | Ops team formally takes over DataHub/DRIA/SageMaker; working team scales down to support | COO/CIO confirm ops team authority + budget | Ops team charter signed; permanent funding approved | Ops handoff complete; permanent team structure
46 | 01/11 - 01/15 | Phase 4 | V1 Program Success Review & Celebration | M46: Retrospective on 12-month journey; document ROI, lessons learned, team recognition, V2 roadmap launch | Team retrospective + all-hands celebration; LOB recognition events | SteerCo final readout + board presentation | Retrospective findings approved; V2 roadmap launched | Program retrospective report; V2 roadmap charter