## Phase 1
Task ID | Task Name | Description | Owner (Role) | Priority | Status | Start Week | End Week | Dependencies | Exit Gate Contribution
P1-01 | Finalize Scoring Framework | Adapt Four Pillars framework (coverage, quality, accessibility, governance) for bank context; validate against BCBS 239 | Data Architect | H | Not Started | 1 | 3 | None | Approved scoring model
P1-02 | Establish Metadata Schema | Define enterprise metadata standard (ISO 11179 compliant); map to FIBO for semantic consistency | Data Architect | H | Not Started | 1 | 4 | P1-01 | Published metadata standard
P1-03 | Set Up DataHub Instance | Deploy & configure Collibra/Alation; integrate with AWS Glue and Snowflake | Data Engineer | H | Not Started | 2 | 5 | None | Live DataHub catalog
P1-04 | Ops LOB Pilot Expansion | Refactor Ops LOB pilot artifacts (data lineage, PII masking rules) for global template | Discovery Analyst | H | Not Started | 1 | 6 | P1-02 | Reusable pilot artifacts
P1-05 | Legacy Mainframe Audit | Crawl COBOL/JCL systems; document data flows, dependencies, transformation logic | Discovery Analyst | H | Not Started | 2 | 8 | None | Mainframe data lineage map
P1-06 | Cloud Data Source Crawl | Automated scan of AWS (S3, Redshift), Snowflake, Databricks; identify tables, columns, owners | Data Engineer | H | Not Started | 3 | 7 | P1-03 | Cloud source inventory
P1-07 | Identify Data Owners (LOB Leads) | Kick-off with 13 LOB heads; assign data stewards and domain owners; establish RACI | Program Lead | H | Not Started | 1 | 4 | None | Signed RACI matrix
P1-08 | Create Business Glossary (Draft) | Define 200+ business terms (e.g., Client, Account, Risk); map to FIBO concepts; get SME sign-off | Data Architect | M | Not Started | 3 | 8 | P1-02 | Draft glossary (80% coverage)
P1-09 | PII/MNPI Classification Rules | Define masking policies per GDPR/CCPA; integrate with AWS Comprehend for auto-detection | Compliance Officer | H | Not Started | 2 | 6 | None | Policy document + Glue rules
P1-10 | Data Quality Baseline Assessment | Sample 50 critical datasets; measure accuracy, completeness, timeliness per BCBS 239 | Discovery Analyst | M | Not Started | 5 | 9 | P1-06,P1-05 | Quality scorecard
P1-11 | Establish Governance Council | Charter SteerCo (exec steering), Tech Council (bi-weekly technical), Risk & Compliance (bi-weekly) | Program Lead | H | Not Started | 1 | 2 | None | Signed charters + schedule
P1-12 | Ops LOB Pilot Scoring | Score Ops LOB datasets using finalized framework; validate scoring methodology | Data Architect | H | Not Started | 4 | 8 | P1-01,P1-04 | Ops LOB pilot scorecard
P1-13 | Create Data Ownership Registry (DRIA) | Set up DRIA tool for data owners to accept responsibility; link to DataHub | Data Engineer | H | Not Started | 4 | 7 | P1-03,P1-07 | DRIA tool live + 50 registrations
P1-14 | Risk Register & BCBS 239 Audit Trail | Document all data lineage changes; create audit logs for regulatory review | Compliance Officer | H | Not Started | 3 | 8 | P1-05,P1-06 | Audit trail proof-of-concept
P1-15 | Vendor RFP (NLP/ML Services) | Issue RFP for entity extraction, classification, sensitivity detection (Phase 3 prep) | Program Lead | M | Not Started | 5 | 10 | None | Vendor shortlist (3-5)
P1-16 | Change Readiness Assessment | Survey 13 LOBs; identify change resistance, skill gaps, cultural drivers | Change Lead | M | Not Started | 6 | 9 | None | Change readiness report
P1-17 | Training Curriculum Draft | Outline DataHub, DRIA, data literacy modules for LOB stewards | Change Lead | M | Not Started | 7 | 11 | P1-16 | Curriculum outline
P1-18 | Security Architecture (Zero Trust) | Define row-level (RLS) and column-level (CLS) access policies; AWS IAM/Snowflake roles | Security Officer | H | Not Started | 3 | 8 | None | Security policy document
P1-19 | Establish KPI Dashboard (Draft) | Define success metrics (# datasets cataloged, % coverage, adoption rate) | Program Lead | M | Not Started | 8 | 11 | None | KPI dashboard template
P1-20 | Phase 1 Exit Gate Review | SteerCo approves Phase 2 readiness; validate scoring framework, data owner engagement, compliance | Program Lead | H | Not Started | 11 | 12 | P1-01 through P1-19 | SteerCo sign-off

## Phase 2
Task ID | Task Name | Description | Owner (Role) | Priority | Status | Start Week | End Week | Dependencies | Exit Gate Contribution
P2-01 | Scoring Engine Architecture | Design automated scoring pipeline (AWS SageMaker/Glue); integrate with DataHub | Data Architect | H | Not Started | 10 | 12 | P1-01,P1-06 | Architecture design doc
P2-02 | Implement Scoring Logic (Automated) | Build data quality rules, coverage scoring, governance compliance checks in SageMaker | ML/NLP Engineer | H | Not Started | 11 | 14 | P2-01 | Scoring engine MVP
P2-03 | Score All 300+ Datasets | Run automated scoring across legacy + cloud sources; generate initial prioritization | Data Engineer | H | Not Started | 13 | 16 | P2-02 | Master scorecard (all datasets)
P2-04 | Data Owner DRIA Acceptance | 100 data owners accept responsibility via DRIA tool; resolve scores via governance meetings | Program Lead | H | Not Started | 14 | 18 | P1-13,P2-03 | Signed DRIA registrations
P2-05 | Conflict Resolution (Scoring Disputes) | Facilitate Tech Council reviews of disputed scores; document rationale | Data Architect | M | Not Started | 15 | 18 | P2-03,P2-04 | Resolution audit trail
P2-06 | Publish Prioritized Backlog | Rank datasets by readiness + business value; publish Phase 3 intake list | Program Lead | H | Not Started | 17 | 19 | P2-04,P2-05 | Prioritized backlog (Phase 3 queue)
P2-07 | Update Business Glossary (100%) | Finalize glossary; cross-map all 300+ datasets to FIBO ontology terms | Data Architect | M | Not Started | 12 | 18 | P1-08 | Complete glossary
P2-08 | Data Quality Remediation Plan | For low-scoring datasets, define DQ improvements + timeline | Discovery Analyst | M | Not Started | 16 | 20 | P2-03 | Remediation roadmap
P2-09 | Sensitivity Scoring Validation | Review PII/MNPI flags; confirm AWS Comprehend accuracy; refine rules | Compliance Officer | H | Not Started | 13 | 17 | P1-09,P2-02 | Validated sensitivity matrix
P2-10 | Lineage Traceability Audit | Verify BCBS 239 lineage for top 50 datasets; ensure provenance tracking works | Compliance Officer | H | Not Started | 14 | 18 | P1-05,P1-06,P2-03 | Lineage audit report
P2-11 | Cost-Benefit Analysis (Phase 3+4) | Model ROI of enrichment, vectorization, change mgmt; present to SteerCo | Program Lead | M | Not Started | 15 | 18 | P2-06 | Business case presentation
P2-12 | Vendor Selection (NLP/ML) | Evaluate RFPs; select vendors for entity extraction, classification, embeddings | Program Lead | H | Not Started | 16 | 20 | P1-15 | Signed contracts + kickoff
P2-13 | SageMaker & AWS Glue Configuration | Set up ML pipelines for Phase 3 enrichment; test data connectors | Data Engineer | H | Not Started | 17 | 21 | P2-01 | Pipeline proof-of-concept
P2-14 | Adoption Metrics Baseline | Measure current state: user engagement, data access patterns, steward responsiveness | Change Lead | M | Not Started | 16 | 19 | P1-19 | Baseline metrics report
P2-15 | SteerCo Checkpoint & Phase 2 Exit Gate | Present prioritized backlog, cost-benefit, Phase 3 plan; get executive alignment | Program Lead | H | Not Started | 18 | 19 | All P2 tasks | SteerCo approval for Phase 3
P2-16 | Training Pilot (DataHub + DRIA) | Run training with Ops LOB + Auto LOB stewards; gather feedback | Change Lead | M | Not Started | 17 | 20 | P1-17,P2-04 | Training feedback report
P2-17 | Risk Register Update (BCBS 239) | Add Phase 2 controls to audit trail; validate compliance posture | Compliance Officer | M | Not Started | 17 | 20 | P1-14,P2-10 | Updated risk register
P2-18 | Establish Data SLAs | Define dataset availability, latency, completeness targets per Data Mesh model | Data Architect | M | Not Started | 18 | 21 | P2-03,P2-06 | SLA framework document
P2-19 | KPI Dashboard (Live) | Publish real-time scoring, adoption, quality metrics; set weekly review cadence | Program Lead | M | Not Started | 19 | 21 | P1-19,P2-14 | Live KPI dashboard
P2-20 | Legal & Regulatory Sign-Off (GDPR/CCPA) | Get legal blessing for consent management, data usage policies | Compliance Officer | H | Not Started | 16 | 22 | P1-09,P2-09 | Legal memo on compliance

## Phase 3
Task ID | Task Name | Description | Owner (Role) | Priority | Status | Start Week | End Week | Dependencies | Exit Gate Contribution
P3-01 | NLP Entity Extraction Pilot | Extract entities (Client, Account, Product) from semi-structured data; validate with SMEs | ML/NLP Engineer | H | Not Started | 18 | 22 | P2-12,P2-13 | Entity extraction model (F1>0.85)
P3-02 | Data Classification & Tagging | Auto-classify datasets (Master Data, Transactional, Reference, Analytics); assign tags | ML/NLP Engineer | H | Not Started | 20 | 24 | P3-01 | Classification taxonomy applied
P3-03 | Sensitivity Detection (NLP) | Use AWS Comprehend + custom models for PII, MNPI, confidential data detection | ML/NLP Engineer | H | Not Started | 19 | 23 | P2-09,P3-01 | Sensitivity detection rules (accuracy>95%)
P3-04 | Vector Embeddings & Semantic Search | Generate vector embeddings (word2vec/transformer) for 300+ datasets; enable semantic search | ML/NLP Engineer | H | Not Started | 22 | 26 | P3-01,P3-02 | Vector store live (Pinecone/FAISS)
P3-05 | Metadata Enrichment Pipeline | Inject: business definitions, lineage, quality scores, ownership, usage rights into DataHub | Data Engineer | H | Not Started | 21 | 25 | P3-02,P3-03 | DataHub 100% enriched metadata
P3-06 | ODRL Policy Attachment | Attach machine-readable usage policies (e.g., 'No AI training on this dataset') to data | Compliance Officer | M | Not Started | 23 | 26 | P3-05 | ODRL policies linked to datasets
P3-07 | Auto-Summarization (Data Descriptions) | Generate summaries of large datasets using abstractive NLP; review with data owners | ML/NLP Engineer | M | Not Started | 24 | 27 | P3-02 | Summaries for 100 critical datasets
P3-08 | DataHub Integration (Complete) | Full bi-directional sync: metadata, lineage, quality scores, policies auto-update | Data Engineer | H | Not Started | 21 | 26 | P3-05 | DataHub fully integrated
P3-09 | DRIA ML Enrichment | Use DRIA to auto-suggest data owners, stewards, and remediation actions based on ML scores | Data Engineer | M | Not Started | 25 | 28 | P3-04,P3-05 | DRIA ML recommendations active
P3-10 | Snowflake/Teradata Tag Sync | Push metadata tags + lineage back to source systems for governed access | Data Engineer | H | Not Started | 26 | 29 | P3-05,P3-08 | Tags visible in Snowflake/Teradata
P3-11 | SageMaker Agent Readiness Check | Validate 50 critical datasets for AI agent consumption (accuracy, lineage, confidence scores) | Data Architect | H | Not Started | 27 | 30 | P3-04,P3-05,P3-10 | Agent-ready certification
P3-12 | Cost Optimization (Data Mesh) | Analyze storage, compute costs across 13 LOBs; recommend consolidation/archiving | Data Engineer | M | Not Started | 25 | 30 | P2-06 | Cost optimization report
P3-13 | Cross-LOB Data Product Onboarding | Facilitate Auto, Credit Card, Risk LOBs to publish data products with SLAs | Program Lead | M | Not Started | 28 | 32 | P3-08,P3-11 | 3+ LOBs with published products
P3-14 | Change Management: Training Rollout | Deploy DataHub, DRIA, new workflows to all 13 LOBs; measure adoption | Change Lead | H | Not Started | 26 | 32 | P2-16,P3-05 | Training completion >80%
P3-15 | Quality Monitoring Automation | Set up continuous data quality checks in SageMaker; alert on degradation | Data Engineer | M | Not Started | 28 | 32 | P3-05 | Live quality monitoring dashboard
P3-16 | Governance Policy Enforcement | Implement automated access controls (RLS/CLS); enforce ODRL policies at query time | Security Officer | H | Not Started | 27 | 31 | P3-06,P3-08 | Policy enforcement live
P3-17 | Compliance Audit Trail (BCBS 239) | Finalize audit logs for all data access, lineage changes, policy decisions | Compliance Officer | H | Not Started | 29 | 33 | P3-05,P3-16 | Audit trail certification
P3-18 | Phase 3 Exit Gate: Agent-Ready Ecosystem | Validate 100+ datasets are AI-agent ready; confirm compliance, security, quality gates pass | Program Lead | H | Not Started | 32 | 34 | All P3 tasks | Executive sign-off on readiness

## Phase 4
Task ID | Task Name | Description | Owner (Role) | Priority | Status | Start Week | End Week | Dependencies | Exit Gate Contribution
P4-01 | LOB Steward Training (Full Roll-Out) | Deliver hands-on DataHub, DRIA, quality ownership training to all 13 LOBs | Change Lead | H | Not Started | 30 | 36 | P3-14 | Training completion >90%
P4-02 | Gamification & Adoption Incentives | Launch quality leaderboard, steward badges, recognition program; measure engagement | Change Lead | M | Not Started | 33 | 38 | P4-01 | Engagement metrics >60%
P4-03 | Operational Monitoring (24/7) | Set up on-call schedules for DataHub, DRIA, SageMaker pipelines; incident response playbooks | Data Engineer | H | Not Started | 35 | 40 | P3-15,P3-17 | SLAs met >99%
P4-04 | Executive Readout Preparation | Compile program results: cost savings, quality uplift, adoption metrics; prepare executive brief | Program Lead | H | Not Started | 39 | 41 | P4-02,P4-03 | Executive brief + board deck
P4-05 | V2 Business Case Development | Model Phase 2 costs/benefits; define Phase 5+ roadmap (AI agents, real-time features) | Program Lead | H | Not Started | 38 | 42 | P4-04 | V2 business case approved
P4-06 | Cross-LOB Innovation Pilots | Identify 3-5 use cases leveraging enriched data (e.g., cross-sell, risk analytics, compliance) | Program Lead | M | Not Started | 36 | 44 | P3-18 | Pilot business cases approved
P4-07 | Data Product Marketplace | Build self-service portal for LOBs to discover, access, and join data products | Data Engineer | M | Not Started | 37 | 42 | P3-13 | Marketplace live
P4-08 | Continuous Improvement Process | Establish sprint-based improvement cycles; prioritize backlog from steward feedback | Program Lead | M | Not Started | 40 | 44 | P4-02 | Improvement process documented
P4-09 | Risk & Compliance Certification | Final audit against BCBS 239, GDPR, CCPA, NIST AI RMF; get regulatory sign-off | Compliance Officer | H | Not Started | 41 | 45 | P3-17,P4-03 | Regulatory certification
P4-10 | Data Mesh Governance Maturity | Assess LOB autonomy + central oversight balance; document operating model | Data Architect | M | Not Started | 40 | 44 | P4-08 | Governance model v1 published
P4-11 | Retirement of Legacy Tools/Processes | Phase out manual spreadsheets, legacy catalogs; migrate to DataHub/DRIA | Program Lead | M | Not Started | 42 | 46 | P4-07 | Legacy systems decommissioned
P4-12 | Knowledge Transfer & Documentation | Codify all decisions, architectures, lessons learned; create runbooks for ops teams | Change Lead | M | Not Started | 43 | 47 | P4-09 | Complete documentation library
P4-13 | Final Stakeholder Alignment | Sync with SteerCo, Tech Council, Risk & Compliance; resolve open items for handoff | Program Lead | H | Not Started | 44 | 46 | All prior phases | All stakeholders signed off
P4-14 | Program Closeout & Transition | Transition from project to ops model; establish permanent governance + team structure | Program Lead | H | Not Started | 46 | 48 | P4-13 | Ops team charter signed
P4-15 | V1 Program Success Review | Hold final retrospective; document ROI, lessons learned, team recognition | Program Lead | M | Not Started | 47 | 48 | P4-14 | Program retrospective report

## Cross-Phase
Task ID | Task Name | Description | Owner (Role) | Priority | Status | Start Week | End Week | Dependencies | Exit Gate Contribution
XP-01 | SteerCo Monthly Steering | Executive steering committee review of program health, risks, budget; monthly cadence weeks 2, 6, 10, 14, ... | Program Lead | H | Not Started | 1 | 48 | None | Executive alignment + decisions
XP-02 | Tech Council Bi-Weekly Syncs | Technical deep-dives on architecture, data design, tool integrations; resolve blockers | Data Architect | H | Not Started | 1 | 48 | None | Technical decisions documented
XP-03 | Risk & Compliance Bi-Weekly Reviews | Audit trail validation, policy enforcement, regulatory alignment; identify new risks | Compliance Officer | H | Not Started | 1 | 48 | None | Compliance sign-off at gates
XP-04 | Daily Standup (Working Team) | Core 7.25 FTE team syncs; track blockers, dependencies, interdependencies across phases | Program Lead | H | Not Started | 1 | 48 | None | Daily progress notes
XP-05 | LOB Steering Touchpoints (Monthly) | 1-on-1 meetings with 13 LOB heads; track data owner engagement, concerns, wins | Program Lead | M | Not Started | 2 | 48 | P1-07 | Engagement tracking + issues log
XP-06 | Risk Register Maintenance | Update BCBS 239 risk register weekly; track emerging risks (data lineage gaps, tool failures) | Compliance Officer | M | Not Started | 1 | 48 | None | Current risk register
XP-07 | Budget & Burn Rate Tracking | Monitor actuals vs. forecast; report to CFO/SteerCo quarterly; manage vendor spend | Program Lead | M | Not Started | 1 | 48 | None | Quarterly budget reviews
XP-08 | Architecture Review Board (ARB) | Quarterly technical architecture reviews; validate security, scalability, GDPR compliance | Data Architect | M | Not Started | 6 | 48 | P1-02,P2-01 | ARB sign-off documents
XP-09 | Vendor Management & SLAs | Monitor Collibra, AWS, Databricks contracts; ensure SLA compliance, escalate issues | Program Lead | M | Not Started | 1 | 48 | None | Vendor scorecard updates
XP-10 | Executive Communications & KPI Reporting | Weekly KPI dashboard updates, monthly status reports, quarterly all-hands; track adoption metrics | Program Lead | H | Not Started | 2 | 48 | P1-19,P2-19 | Status reports + KPI dashboards
XP-11 | Data Security & Privacy Audits | Quarterly penetration testing, access reviews, data residency checks; remediate findings | Security Officer | M | Not Started | 4 | 48 | P1-18,P3-16 | Audit reports + remediation
XP-12 | Lessons Learned & Continuous Improvement | Bi-weekly retrospectives on phase milestones; document best practices, update playbooks | Change Lead | M | Not Started | 8 | 48 | All phases | Playbook updates + lessons library